## Slide 1: Election Management Plan

## Slide 2: District Election Management Plan (DEMP)
Not a strategic plan but an operational plan.
Focus is on implementation of the plan to ensure free & fair elections.
A single window for all relevant information.
Synergies activities in a time bound manner.

## Slide 3: COMPONENTS of DEMP
DEMP
District Profile
Elector Details
Polling Stations
Sector Plan
Movement Plan
Police Deployment Plan
Communication Plan
Counting Plan
Personnel Management Plan
SVEEP
Training Plan
Expenditure Monitoring Plan
Vulnarabillity & Sensitivity Analysis

## Slide 4: Components of DEMP
  Important Officials and contact details
  Geography
  Demography
  Administrative Units (including constituencies)
  Mapping of administrative units-Constituency-District-Assembly
  segment-Block/Municipality-Police station
  General Law & order, history of district
  Past electoral offences, action taken, pending cases

## Slide 5
Elector Details
  Gender Ratio
  Elector-Population Ratio(E-P ratio)
  Inclusion & Deletion
  EPIC Coverage
  Availability of electoral roll related information in public domain for benefit of electors

## Slide 6: Polling Stations
Whether all polling stations of the district conform to ECI instruction w.r.t access, condition, ownership of the building,
Whether any auxiliary polling station will be required in case the electors assigned to any polling station is more than the stipulated number of polling stations,
Whether Assured Minimum Facilities at all polling stations could be guaranteed as mandated by the ECI, plan for meeting up the gaps ,thereof,
Plan for making polling stations ready for taking poll well in advance,
Information on polling station to be made available in public domain for benefit of electors.

## Slide 7: VULNERABILITY MAPPING
IDENTIFY VULNERABLE AREAS, POLLING STATION-WISE
IDENTIFY SOURCE OF THREAT/ INTIMIDATION
IDENTIFY NAMES OF PERSONS LIKELY TO SPEARHEAD SUCH OFFENCE OF UNDUE INFLUENCE
TAKE INTO COGNIZANCE PAST INCIDENTS AND PRESENT APPREHENSIONS
IDENTIFY POINTS OF CONTACT
INITIATE PREVENTIVE/ CONFIDENCE BUILDING MEASURES

## Slide 8: CRITICALITY ANALYSIS
IDENTIFY CRITICAL POLLING STATIONS
  HIGHER NUMBER OF NON-EPIC ELECTORS
  HIGHER NUMBER OF MISSING VOTERS WITHOUT FAMILY LINKAGE
  POLLING STATIONS HAVING VULNERABLE POCKETS
  ABOVE 90% VOTES POLLED OUT OF WHICH ABOVE 75% IN FAVOUR OF A PARTICULAR CANDIDATE
  RE-POLL REPORTED DUE TO MALPRACTICES, AND WHERE ELECTORAL VIOLENCE HAS TAKEN PLACE DURING LAST ELECTION
TO BE DONE BY DEO/ POLICE TO PROVIDE INPUTS ON 3 & 5

## Slide 9
Personnel includes
Personnel in Statutory posts
Sector Personnel
Personnel of different functional Cells
EVM Ground Staff
Polling Personnel
Micro Observer
Voters Assistance Booth Personnel
Digital/ Still / Web Camera Personnel
Videographers
Expenditure Monitoring Personnel including Asst. Exp. Observers
Counting Personnel
The District Plan will contain the category wise requirement of each of the above
PERSONNEL MANAGEMENT PLAN

## Slide 10: Training matters
Details of schedule for training for all categories of election related personnel
Assessment and mobilizing details of the Resource Persons (RP)
Outlay of Training Plan
Availability of suitable training venues
Availability of training materials, circulation etc.
Provision for availability of training material in vernacular

## Slide 11: Sector Arrangement
Civil Sector- cluster of polling stations in close contiguous geographical proximity
To be formed in advance in consultation with the police and co-terminus with the police sector
To be used for identification od Vulnerable moujas, sensitive polling stations and remedial action through Confidence Building Measures(CBM)
Facilitation of electors,providing information and ensuring confidence
EVM awareness
Field level monitoring of MCC & Expenditure related violations of norms.

## Slide 12: Polling Personnel welfare measures
Name, Designation and contact details of nodal officer in charge of ensuring polling personnel welfare
Clear communication of training schedule, dispatching schedule
Basic amenities at training and dispatching venue
Facilities at PS to be physically verified and ensured - Adequate facilities for food, refreshments and medical requirements to be made
Immediate relieving from duty after handover of EVMs and polling materials
Advance measures to ensure transport facilities for staff
Special facilities/measures for physically challenged, female polling personnel, death of personnel on duty

## Slide 13: EVM & materials management
Assessment of requirement of EVM/VVPAT & all election materials as per scale of requirement
Provision of inventory of existing usable stock
Assessment for fresh procurement
Time schedule for procurement & official formalities, thereof
Identification of storage space of procured materials
Plan for distribution
Plan for bagging of materials as per requirement

## Slide 14: Movement Plan
Movement plan for polling parties with route charts (keeping in mind the newly formed polling stations due to rationalsiation).
Sector wise planning
Also alternative routes
Sketch Map of Constituency showing sector routes
Assessment of vehicle requirements
Tapping sources wherefrom the vehicles can be mobilized to meet the requirement
Contingency plan for vulnerable areas eg hilly terrain, riverine areas, islands, remote jungle areas

## Slide 15: Expenditure Monitoring Matters
Detailment of Expenditure Monitoring Teams:
Expenditure Observer
Asst. Expenditure Observer
Flying Squad and Static Surveillance Teams
Video Surveillance Team
Video Viewing Team
Media Certification and Monitoring Committee
Accounting Team
Call Center/Control Room
Released of Seized articles team
Associating Income Tax Department
Excise Directorate.

## Slide 16: Communication Plan
DEO, RO,AROs LANDLINE/MOBILE No.
DISTRICT LEVEL HELPLINE(24X7) FOR COMPLAINT MONITORING
List of landline and cellular connections available near each PS
along with particulars of contact person
List of polling personnel/ SO with cellular numbers
Plan mode of communication such as VHF/HF to ensure connectivity in mobile shadow regions
Identification of mobile /web network shadow zone
Identification of first referral point in case of hospital need of a polling personnel.

## Slide 17: Single Window System
ECI No. 464/INST/2014/EPS dated: 20.03.2014 & 03.04.2014
SINGLE WINDOW SYSTEM to be set up at the Sub-Divisional Level (for Outlying sub-divisions) and at DEO’s end for Sadar sub-division of concerned District during the election period, to grant permissions to the political parties and candidates for -
a) usage of non-commercial/remote/uncontrolled airports/helipads;
b) organizing public meetings/rallies/ processions, use of loudspeakers;
c) use of vehicles for election campaigning.

## Slide 18: Composition of Single Window System
Single Window System Officers: (At Sub-divisional level)
Police Officer (not below the rank of Inspector- Nodal Officer
Representative of SDO(not below the rank of DMDC)
Executive Engineer of Municipalities/Corporation for according permission for use of Municipality/corporation holding/land.
Assistant Divisional Fire Officer
Assistant Engineer WBSEDCL
Assistant Engineer PWD Civil/PWD Roads
ACMOH
Representative of Regional Transport Officer
Single Window System Officers for Helipad permission: (At District level)
Additional district Magistrate (duly authorized by the DEO)
Representative of SDO (not below the rank of DMDC)
Police Officer (not below the rank of DSP)- Nodal Officer
District Engineer Zilla Parishad
Executive Engineer of Municipalities/Corporation for according permission for use of Municipality/corporation holding/land.
Divisional Fire Officer
Executive Engineer PWD Civil/PWD Roads
Dy. CMOH
Executive Engineer WBSEDCL
Regional Transport Officer

## Slide 19: Force measures
Assessment of requirement of police personnel (various ranks)
For sector movement and to man polling stations
Prepare return journey for polled EVMs/Polling material, their storage and security plan till counting
Guarding strategic locations eg DC RC CC
For deployment in FS/SST/MCC team

## Slide 20: Non force measures
Assessment of requirement of digital cameras/video cameras
Identification of polling stations where online web casting can be done
Identification of polling stations where offline web casting (through CCTV) can be done
Identification of sources wherefrom those can be mobilised

## Slide 21: Infrastructural facilities
Selection of Dispersal Centre, Receiving Centre and Counting Centre ( Ideally co-terminous and within constituency area)
Transit RC or Collection Centre ( if required)
Selection of Training Centres
Selection of centres for taking up FLC, Commissioning of EVMs/VVPATs
Selection of warehouses and strong rooms
Availability of basic facilities at those centres viz DW/Electricity with back up/Net working & communication facility/proper sanitation/good approach road etc.

## Slide 22: SVEEP & Awareness Plan
Emphasis on:
Participation of registered voters in voting process,
Ethical voting,
Use of EVM VVPAT ensuring correctness of vote recording.

## Slide 23
Aims to develop various strategies for wide-scale dissemination of information providing
electoral assistance
developing cultural habit of voting
helping voters overcome psychological barrier,
reaching out to youth voter in colleges and universities
Special plan targeting low VTR polling stations
increasing women participation
promoting election watch and democracy platforms
designing communication campaign,
designing and producing communication materials on pilot basis and
quality control of state level products
Promoting ethical voting
Target oriented detailed plan of using multi media approach upto polling station level and schedule thereof

## Slide 24: Counting Plans
Identify places for storage of EVMs & Polling materials
Submit Proposal to CEO for approval from ECI in advance
Assess Counting Staff availability
Detail other logistics, media and security arrangements

## Slide 25: Budgeting and Financial planning
Under the instruction of the Ministry of Law , Justice & Company Affairs (Legislative Department) ,Government of India, the entire expenditure on actual conduct of elections to state legislatures is borne by the respective State Governments when such elections are held independently.
Expenditure incurred on items of common concern to the Central and State Governments is shared on 50:50 basis irrespective of whether such expenditure is incurred in connection with the elections to Loksabha or State Legislatures.
Expenditures made on account of maintenance of security is borne by the State Government.
Expenditure made by the candidates and political parties which is subject to a ceiling limit, as fixed by the central legislature is to be maintained by the candidates and political parties themselves in prescribed manner and reported to the Election Commission.
Planning and budgeting: Since conduct of elections is a mammoth task involving mobilization of resources - both human & materials, meticulous planning is required in advance of the elections.
A detailed assessment of fund required for the conduct of elections is to be made .

## Slide 26
Items of expenditures: The assessment of expenditures included the following items which are essentially required for conduct of elections:
1.a. Checking of EVMs
b. Transportation of EVMs- inter state , inter district & intra district
c. Logistic arrangement for FLC, Commissioning
d. Procurement of power packs
e. Expert charges to ECIL engineers
2.a. Procurement of all kinds of seals, indelible ink ,tags, arrow cross marks etc.
b. Procurement of materials for EVM commissioning/polling/counting
c. Manpower charges for material bagging
d. Cost of stationery articles

## Slide 27
Items of expenditures:
3.a. Allowances of polling personnel, Micro Observer, camera persons, VAB
personnel, water carriers, Expenditure monitoring teams, sectors, DCRC
personnel, counting personnel etc.
b Honorarium/ Allowances to officers, staff
4. a. Hiring charges of Vehicles - for polling personnel, other personnel
b. Khoraki charges
c. Fuel charges
5. IT initiatives- Web casting, sms gateway, vehicle management, Live monitoring
in sensitive areas etc.
6. Printing of forms, book, ballot papers ( service ballot/braille)
7. Photocopying of electoral rolls, Preparation of Voters slips
8. Publicity, SVEEP initiatives

## Slide 28
9. Videography, documentation
10. Infrastructural arrangement for training, DCRC, Counting, Strong Room
11. Polling station infrastructure
12. Removal of MCC violations
13. Refreshment charges
14. Logistics for Observers
15. Call centre, complaint help line
16.Compensation to personnel-dead or injured during poll duties ( ex gratia)
Emphasis on :
Maintenance of financial propriety .
Strict adherence to financial rules.
Exploring methods for curbing misuse of fund through exercising strict financial discipline.
Adopting innovative approach to restrict expenditure.

## Slide 29: Constituency Plan –In similar manner

## Slide 30: THANK YOU